## HELP
Phase 1: PROJECT SETUP | WHO
1.1 Update the GANTT sheet (try to use the same format and avoid spaces in the partner list) | COORDINATOR
1.2 Update the summary tables in ACTUAL/PLANNED/MONITORING sheets | COORDINATOR
1.3 Rename/Add/remove all the sheets after the GANTT using the same names used in the GANTT partner list | COORDINATOR
Phase 2: PROJECT MONITORING | WHO
2.1 Collect every actual efforts updating the values in the PARTNER sheet | EACH PARTNER
Phase 3: PROJECT MONITORING | WHO
3.1 Use the summary tables and charts from the MONITORING sheets for reporting | COORDINATOR

## MONITORING_VS_TOTAL
| M4 |  |  | M8 |  |  | M12 |  |  | M16 |  |  | M20 |  |  | M24 |  |  | M28 |  |  | M24 |  |  | M27 |  |  | M30 |  |  | M33 |  |  | M36 |  |  | M32 |  |  | M36
| PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF= Project Funded
ENG | 123 | 0 | 0% | 123 | 0 | 0% | 123 | 0 | 0% | 123 | 0 | 0% | 123 | 0 | 0% | 123 | 0 | 0% | 123 | 0 | 0% | 65.5702 | 0 | 0% | 74.552 | 0 | 0% | 81.0793 | 0 | 0% | 87.4995 | 0 | 0% | 91 | 0 | 0% | 123 | 0 | 0% | 123 | 0 | 0% | AC= Actual Effort Spent
CERTH | 75 | 0 | 0% | 75 | 0 | 0% | 75 | 0 | 0% | 75 | 0 | 0% | 75 | 0 | 0% | 75 | 0 | 0% | 75 | 0 | 0% | 29.6149 | 0 | 0% | 33.0764 | 0 | 0% | 36.1289 | 0 | 0% | 37.3867 | 0 | 0% | 38 | 0 | 0% | 75 | 0 | 0% | 75 | 0 | 0%
RiSSC | 46 | 0 | 0% | 46 | 0 | 0% | 46 | 0 | 0% | 46 | 0 | 0% | 46 | 0 | 0% | 46 | 0 | 0% | 46 | 0 | 0% | 14.9502 | 0 | 0% | 17.3843 | 0 | 0% | 19.8184 | 0 | 0% | 22.1161 | 0 | 0% | 24 | 0 | 0% | 46 | 0 | 0% | 46 | 0 | 0%
EXPSYS | 69 | 0 | 0% | 69 | 0 | 0% | 69 | 0 | 0% | 69 | 0 | 0% | 69 | 0 | 0% | 69 | 0 | 0% | 69 | 0 | 0% | 19.9275 | 0 | 0% | 23.0812 | 0 | 0% | 26.2349 | 0 | 0% | 28.9795 | 0 | 0% | 31 | 0 | 0% | 69 | 0 | 0% | 69 | 0 | 0%
AIT | 38 | 0 | 0% | 38 | 0 | 0% | 38 | 0 | 0% | 38 | 0 | 0% | 38 | 0 | 0% | 38 | 0 | 0% | 38 | 0 | 0% | 28.692 | 0 | 0% | 32.2102 | 0 | 0% | 33.4102 | 0 | 0% | 34.6103 | 0 | 0% | 35.5 | 0 | 0% | 38 | 0 | 0% | 38 | 0 | 0%
IBEC | 48 | 0 | 0% | 48 | 0 | 0% | 48 | 0 | 0% | 48 | 0 | 0% | 48 | 0 | 0% | 48 | 0 | 0% | 48 | 0 | 0% | 28.2766 | 0 | 0% | 32.2624 | 0 | 0% | 36.2482 | 0 | 0% | 39.3741 | 0 | 0% | 42.5 | 0 | 0% | 48 | 0 | 0% | 48 | 0 | 0%
IIP | 27 | 0 | 0% | 27 | 0 | 0% | 27 | 0 | 0% | 27 | 0 | 0% | 27 | 0 | 0% | 27 | 0 | 0% | 27 | 0 | 0% | 38.4609 | 0 | 0% | 42.0639 | 0 | 0% | 44.7124 | 0 | 0% | 46.27 | 0 | 0% | 47 | 0 | 0% | 27 | 0 | 0% | 27 | 0 | 0%
SYSTRAN | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 26.7296 | 0 | 0% | 30.2131 | 0 | 0% | 32.4693 | 0 | 0% | 34.297 | 0 | 0% | 35 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0%
TIU-JADS | 25 | 3.2 | 12.8% | 25 | 4 | 16% | 25 | 4 | 16% | 25 | 4 | 16% | 25 | 4 | 16% | 25 | 4 | 16% | 25 | 4 | 16% | 34.505 | 4 | 11.59% | 37.7099 | 4 | 10.61% | 40.9148 | 4 | 9.776% | 43.5197 | 4 | 9.191% | 45 | 4 | 8.889% | 25 | 4 | 16% | 25 | 4 | 16%
DITSS | 23 | 0 | 0% | 23 | 0 | 0% | 23 | 0 | 0% | 23 | 0 | 0% | 23 | 0 | 0% | 23 | 0 | 0% | 23 | 0 | 0% | 27.5284 | 0 | 0% | 30.4499 | 0 | 0% | 33.3714 | 0 | 0% | 36.1857 | 0 | 0% | 39 | 0 | 0% | 23 | 0 | 0% | 23 | 0 | 0%
VIAS | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 20.6437 | 0 | 0% | 24.1724 | 0 | 0% | 27.7011 | 0 | 0% | 31.2299 | 0 | 0% | 33 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0%
KWPG | 18 | 0 | 0% | 18 | 0 | 0% | 18 | 0 | 0% | 18 | 0 | 0% | 18 | 0 | 0% | 18 | 0 | 0% | 18 | 0 | 0% | [15 empty] | 18 | 0 | 0% | 18 | 0 | 0%
AoC | 26 | 0 | 0% | 26 | 0 | 0% | 26 | 0 | 0% | 26 | 0 | 0% | 26 | 0 | 0% | 26 | 0 | 0% | 26 | 0 | 0% | [15 empty] | 26 | 0 | 0% | 26 | 0 | 0%
CAST | 21 | 0 | 0% | 21 | 0 | 0% | 21 | 0 | 0% | 21 | 0 | 0% | 21 | 0 | 0% | 21 | 0 | 0% | 21 | 0 | 0% | [15 empty] | 21 | 0 | 0% | 21 | 0 | 0%
NPN | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | 13 | 0 | 0% | [15 empty] | 13 | 0 | 0% | 13 | 0 | 0%
GDCOC | 15 | 0 | 0% | 15 | 0 | 0% | 15 | 0 | 0% | 15 | 0 | 0% | 15 | 0 | 0% | 15 | 0 | 0% | 15 | 0 | 0% | [15 empty] | 15 | 0 | 0% | 15 | 0 | 0%
LPV | 12 | 0 | 0% | 12 | 0 | 0% | 12 | 0 | 0% | 12 | 0 | 0% | 12 | 0 | 0% | 12 | 0 | 0% | 12 | 0 | 0% | 41.7491 | 0 | 0% | 45.8404 | 0 | 0% | 49.2498 | 0 | 0% | 51.352 | 0 | 0% | 53 | 0 | 0% | 12 | 0 | 0% | 12 | 0 | 0%
| M4 |  |  | M8 |  |  | M12 |  |  | M16 |  |  | M20 |  |  | M24 |  |  | M28 |  |  | M24 |  |  | M27 |  |  | M30 |  |  | M33 |  |  | M36 |  |  | M32 |  |  | M36
| PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA | PF | AC | DELTA
WP1 | 47 | 0 | 0% | 47 | 0 | 0% | 47 | 0 | 0% | 47 | 0 | 0% | 47 | 0 | 0% | 47 | 0 | 0% | 47 | 0 | 0% | 25.6667 | 0 | 0% | 28.875 | 0 | 0% | 32.0833 | 0 | 0% | 35.2917 | 0 | 0% | 38.5 | 0 | 0% | 47 | 0 | 0% | 47 | 0 | 0%
WP2 | 53 | 0 | 0% | 53 | 0 | 0% | 53 | 0 | 0% | 53 | 0 | 0% | 53 | 0 | 0% | 53 | 0 | 0% | 53 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 53 | 0 | 0% | 53 | 0 | 0%
WP3 | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0% | 144.9327 | 0 | 0% | 157.08 | 0 | 0% | 159 | 0 | 0% | 159 | 0 | 0% | 159 | 0 | 0% | 28 | 0 | 0% | 28 | 0 | 0%
WP4 | 36 | 0 | 0% | 36 | 0 | 0% | 36 | 0 | 0% | 36 | 0 | 0% | 36 | 0 | 0% | 36 | 0 | 0% | 36 | 0 | 0% | 48.0455 | 0 | 0% | 52.1364 | 0 | 0% | 55 | 0 | 0% | 55 | 0 | 0% | 55 | 0 | 0% | 36 | 0 | 0% | 36 | 0 | 0%
WP5 | 47 | 3.2 | 6.809% | 47 | 4 | 8.511% | 47 | 4 | 8.511% | 47 | 4 | 8.511% | 47 | 4 | 8.511% | 47 | 4 | 8.511% | 47 | 4 | 8.511% | 83.5686 | 4 | 4.786% | 97.4457 | 4 | 4.105% | 111.3229 | 4 | 3.593% | 118 | 4 | 3.39% | 118 | 4 | 3.39% | 47 | 4 | 8.511% | 47 | 4 | 8.511%
WP6 | 68 | 0 | 0% | 68 | 0 | 0% | 68 | 0 | 0% | 68 | 0 | 0% | 68 | 0 | 0% | 68 | 0 | 0% | 68 | 0 | 0% | 74.4558 | 0 | 0% | 89.816 | 0 | 0% | 105.1762 | 0 | 0% | 120.5364 | 0 | 0% | 130 | 0 | 0% | 68 | 0 | 0% | 68 | 0 | 0%
WP7 | 65 | 0 | 0% | 65 | 0 | 0% | 65 | 0 | 0% | 65 | 0 | 0% | 65 | 0 | 0% | 65 | 0 | 0% | 65 | 0 | 0% | 51.9234 | 0 | 0% | 61.389 | 0 | 0% | 70.8545 | 0 | 0% | 78.9273 | 0 | 0% | 87 | 0 | 0% | 65 | 0 | 0% | 65 | 0 | 0%
WP8 | 52 | 0 | 0% | 52 | 0 | 0% | 52 | 0 | 0% | 52 | 0 | 0% | 52 | 0 | 0% | 52 | 0 | 0% | 52 | 0 | [16 empty] | 52 | 0 | 0% | 52 | 0 | 0%
WP9 | 58 | 0 | 0% | 58 | 0 | 0% | 58 | 0 | 0% | 58 | 0 | 0% | 58 | 0 | 0% | 58 | 0 | 0% | 58 | 0 | [16 empty] | 58 | 0 | 0% | 58 | 0 | 0%
WP10 | 87 | 0 | 0% | 87 | 0 | 0% | 87 | 0 | 0% | 87 | 0 | 0% | 87 | 0 | 0% | 87 | 0 | 0% | 87 | 0 | [16 empty] | 87 | 0 | 0% | 87 | 0 | 0%
WP11 | 79 | 0 | 0% | 79 | 0 | 0% | 79 | 0 | 0% | 79 | 0 | 0% | 79 | 0 | 0% | 79 | 0 | 0% | 79 | 0 | 0% | 64.8012 | 0 | 0% | 73.4759 | 0 | 0% | 82.1506 | 0 | 0% | 90.8253 | 0 | 0% | 99.5 | 0 | 0% | 79 | 0 | 0% | 79 | 0 | 0%

## ACTUAL
DO NOT EDIT THE FIRST TABLE IN RED!! PLEASE ADD ONE TABLE IN DARK YELLOW FOR EACH PARTNER
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
ALL | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP1 | [36 empty] | 0
WP2 | [36 empty] | 0
WP3 | [36 empty] | 0
WP4 | [36 empty] | 0
WP5 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | [31 empty] | 4
WP6 | [36 empty] | 0
WP7 | [36 empty] | 0
WP8 | [36 empty] | 0
WP9 | [36 empty] | 0
WP10 | [36 empty] | 0
WP11 | [36 empty] | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
ENG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
CERTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
RiSSC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
EXPSYS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
AIT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
IBEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
IIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
SYSTRAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
TIU-JADS | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
DITSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
VIAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
KWPG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
AoC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
CAST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
NPN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
GDCOC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
LPV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## FUNDED
DO NOT EDIT THE FIRST TABLE IN RED!! PLEASE ADD ONE TABLE IN DARK YELLOW FOR EACH PARTNER
| ENG | CERTH | RiSSC | EXPSYS | AIT | IBEC | IIP | SYSTRAN | TIU-JADS | DITSS | VIAS | KWPG | AoC | CAST | NPN | GDCOC | LPV | Total
| 123 | 75 | 46 | 69 | 38 | 48 | 27 | 28 | 25 | 23 | 13 | 18 | 26 | 21 | 13 | 15 | 12 | 620
WP1 | 23 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 1 | 1 | 47
WP2 | 2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 53
WP3 | 3 | 3 |  |  |  |  | 22 | [10 empty] | 28
WP4 | 6 | 8 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 36
WP5 | 8 |  | 2 | 9 | 20 |  |  |  | 8 | [8 empty] | 47
WP6 | 6 | 19 |  | 18 |  |  |  | 17 | 8 | [8 empty] | 68
WP7 | 24 | 12 |  | 24 | 5 | [12 empty] | 65
WP8 | 0 | 18 |  | 1 |  | 32 |  | 1 | [9 empty] | 52
WP9 | 40 | 2 |  | 4 | 3 | 5 |  | 2 | 2 | [8 empty] | 58
WP10 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 11 | 7 | 8 | 10 | 6 | 5 | 6 | 4 | 87
WP11 | 7 | 4 | 8 | 6 | 3 | 4 | 1 | 3 | 3 | 6 | 3 | 5 | 11 | 5 | 3 | 4 | 3 | 79

## MONITORING (hidden)
| M4 |  |  | M8 |  |  | M12 |  |  | M16 |  |  | M20 |  |  | M24 |  |  | M28 |  |  | M24 |  |  | M27 |  |  | M30 |  |  | M33 |  |  | M36 |  |  | M32 |  |  | M36
| PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA
ENG | 6.6783 | 0 | 0% | 17.8484 | 0 | 0% | 29.7338 | 0 | 0% | 41.6187 | 0 | 0% | 53.5944 | 0 | 0% | 65.5702 | 0 | 0% | 76.7278 | 0 | 0% | 65.5702 | 0 | 0% | 74.552 | 0 | 0% | 81.0793 | 0 | 0% | 87.4995 | 0 | 0% | 91 | 0 | 0% | 85.3594 | 0 | 0% | 91 | 0 | 0%
CERTH | 3.863 | 0 | 0% | 8.2227 | 0 | 0% | 13.6779 | 0 | 0% | 18.9903 | 0 | 0% | 24.3026 | 0 | 0% | 29.6149 | 0 | 0% | 34.0939 | 0 | 0% | 29.6149 | 0 | 0% | 33.0764 | 0 | 0% | 36.1289 | 0 | 0% | 37.3867 | 0 | 0% | 38 | 0 | 0% | 36.9675 | 0 | 0% | 38 | 0 | 0%
RiSSC | 2.1223 | 0 | 0% | 3.8765 | 0 | 0% | 5.5775 | 0 | 0% | 8.4593 | 0 | 0% | 11.7048 | 0 | 0% | 14.9502 | 0 | 0% | 18.1956 | 0 | 0% | 14.9502 | 0 | 0% | 17.3843 | 0 | 0% | 19.8184 | 0 | 0% | 22.1161 | 0 | 0% | 24 | 0 | 0% | 21.3502 | 0 | 0% | 24 | 0 | 0%
EXPSYS | 2.289 | 0 | 0% | 4.5892 | 0 | 0% | 7.1764 | 0 | 0% | 11.1843 | 0 | 0% | 15.5559 | 0 | 0% | 19.9275 | 0 | 0% | 24.1325 | 0 | 0% | 19.9275 | 0 | 0% | 23.0812 | 0 | 0% | 26.2349 | 0 | 0% | 28.9795 | 0 | 0% | 31 | 0 | 0% | 28.0647 | 0 | 0% | 31 | 0 | 0%
AIT | 4.0098 | 0 | 0% | 9.9281 | 0 | 0% | 14.619 | 0 | 0% | 19.31 | 0 | 0% | 24.001 | 0 | 0% | 28.692 | 0 | 0% | 32.6102 | 0 | 0% | 28.692 | 0 | 0% | 32.2102 | 0 | 0% | 33.4102 | 0 | 0% | 34.6103 | 0 | 0% | 35.5 | 0 | 0% | 34.2103 | 0 | 0% | 35.5 | 0 | 0%
IBEC | 3.2003 | 0 | 0% | 7.3866 | 0 | 0% | 11.7881 | 0 | 0% | 16.9812 | 0 | 0% | 22.6289 | 0 | 0% | 28.2766 | 0 | 0% | 33.591 | 0 | 0% | 28.2766 | 0 | 0% | 32.2624 | 0 | 0% | 36.2482 | 0 | 0% | 39.3741 | 0 | 0% | 42.5 | 0 | 0% | 38.3321 | 0 | 0% | 42.5 | 0 | 0%
IIP | 4.1515 | 0 | 0% | 9.8459 | 0 | 0% | 16.6396 | 0 | 0% | 23.9134 | 0 | 0% | 31.1871 | 0 | 0% | 38.4609 | 0 | 0% | 42.9468 | 0 | 0% | 38.4609 | 0 | 0% | 42.0639 | 0 | 0% | 44.7124 | 0 | 0% | 46.27 | 0 | 0% | 47 | 0 | 0% | 45.7508 | 0 | 0% | 47 | 0 | 0%
SYSTRAN | 2.1421 | 0 | 0% | 6.8262 | 0 | 0% | 11.7956 | 0 | 0% | 16.713 | 0 | 0% | 21.7213 | 0 | 0% | 26.7296 | 0 | 0% | 30.9652 | 0 | 0% | 26.7296 | 0 | 0% | 30.2131 | 0 | 0% | 32.4693 | 0 | 0% | 34.297 | 0 | 0% | 35 | 0 | 0% | 33.6877 | 0 | 0% | 35 | 0 | 0%
TIU-JADS | 4.245 | 3.2 | 75.38% | 9.8754 | 4 | 40.5% | 15.6854 | 4 | 25.5% | 21.7162 | 4 | 18.42% | 28.1106 | 4 | 14.23% | 34.505 | 4 | 11.59% | 38.7782 | 4 | 10.32% | 34.505 | 4 | 11.59% | 37.7099 | 4 | 10.61% | 40.9148 | 4 | 9.776% | 43.5197 | 4 | 9.191% | 45 | 4 | 8.889% | 42.6514 | 4 | 9.378% | 45 | 4 | 8.889%
DITSS | 5.5247 | 0 | 0% | 9.4408 | 0 | 0% | 13.8426 | 0 | 0% | 18.2833 | 0 | 0% | 22.9059 | 0 | 0% | 27.5284 | 0 | 0% | 31.4237 | 0 | 0% | 27.5284 | 0 | 0% | 30.4499 | 0 | 0% | 33.3714 | 0 | 0% | 36.1857 | 0 | 0% | 39 | 0 | 0% | 35.2476 | 0 | 0% | 39 | 0 | 0%
VIAS | 1.5556 | 0 | 0% | 4.8238 | 0 | 0% | 7.5287 | 0 | 0% | 11.2337 | 0 | 0% | 15.9387 | 0 | 0% | 20.6437 | 0 | 0% | 25.3487 | 0 | 0% | 20.6437 | 0 | 0% | 24.1724 | 0 | 0% | 27.7011 | 0 | 0% | 31.2299 | 0 | 0% | 33 | 0 | 0% | 30.0536 | 0 | 0% | 33 | 0 | 0%
KWPG
AoC
CAST
NPN
GDCOC
LPV | 6.1389 | 0 | 0% | 14.0462 | 0 | 0% | 20.8388 | 0 | 0% | 27.5665 | 0 | 0% | 34.6578 | 0 | 0% | 41.7491 | 0 | 0% | 46.9768 | 0 | 0% | 41.7491 | 0 | 0% | 45.8404 | 0 | 0% | 49.2498 | 0 | 0% | 51.352 | 0 | 0% | 53 | 0 | 0% | 50.6513 | 0 | 0% | 53 | 0 | 0%
| M4 |  |  | M8 |  |  | M12 |  |  | M16 |  |  | M20 |  |  | M24 |  |  | M28 |  |  | M24 |  |  | M27 |  |  | M30 |  |  | M33 |  |  | M36 |  |  | M32 |  |  | M36
| PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA | PV | AC | DELTA
WP1 | 4.2778 | 0 | 0% | 8.5556 | 0 | 0% | 12.8333 | 0 | 0% | 17.1111 | 0 | 0% | 21.3889 | 0 | 0% | 25.6667 | 0 | 0% | 29.9444 | 0 | 0% | 25.6667 | 0 | 0% | 28.875 | 0 | 0% | 32.0833 | 0 | 0% | 35.2917 | 0 | 0% | 38.5 | 0 | 0% | 34.2222 | 0 | 0% | 38.5 | 0 | 0%
WP2 | 53.7857 | 0 | 0% | 87.8571 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0%
WP3 | 6.1818 | 0 | 0% | 30.6927 | 0 | 0% | 59.2527 | 0 | 0% | 87.8127 | 0 | 0% | 116.3727 | 0 | 0% | 144.9327 | 0 | 0% | 157.72 | 0 | 0% | 144.9327 | 0 | 0% | 157.08 | 0 | 0% | 159 | 0 | 0% | 159 | 0 | 0% | 159 | 0 | 0% | 159 | 0 | 0% | 159 | 0 | 0%
WP4 | 3.3333 | 0 | 0% | 8.8939 | 0 | 0% | 18.6818 | 0 | 0% | 28.4697 | 0 | 0% | 38.2576 | 0 | 0% | 48.0455 | 0 | 0% | 53.0909 | 0 | 0% | 48.0455 | 0 | 0% | 52.1364 | 0 | 0% | 55 | 0 | 0% | 55 | 0 | 0% | 55 | 0 | 0% | 55 | 0 | 0% | 55 | 0 | 0%
WP5 | 0 | 3.2 |  | 9.5571 | 4 | 41.85% | 28.06 | 4 | 14.26% | 46.5629 | 4 | 8.591% | 65.0657 | 4 | 6.148% | 83.5686 | 4 | 4.786% | 102.0714 | 4 | 3.919% | 83.5686 | 4 | 4.786% | 97.4457 | 4 | 4.105% | 111.3229 | 4 | 3.593% | 118 | 4 | 3.39% | 118 | 4 | 3.39% | 115.7743 | 4 | 3.455% | 118 | 4 | 3.39%
WP6 | 0 | 0 |  | 7.8621 | 0 | 0% | 16.9241 | 0 | 0% | 33.4953 | 0 | 0% | 53.9755 | 0 | 0% | 74.4558 | 0 | 0% | 94.9361 | 0 | 0% | 74.4558 | 0 | 0% | 89.816 | 0 | 0% | 105.1762 | 0 | 0% | 120.5364 | 0 | 0% | 130 | 0 | 0% | 115.4163 | 0 | 0% | 130 | 0 | 0%
WP7 | 0.92857 | 0 | 0% | 4.9857 | 0 | 0% | 15.2429 | 0 | 0% | 26.6818 | 0 | 0% | 39.3026 | 0 | 0% | 51.9234 | 0 | 0% | 64.5442 | 0 | 0% | 51.9234 | 0 | 0% | 61.389 | 0 | 0% | 70.8545 | 0 | 0% | 78.9273 | 0 | 0% | 87 | 0 | 0% | 76.2364 | 0 | 0% | 87 | 0 | 0%
WP8
WP9
WP10
WP11 | 8.1078 | 0 | 0% | 18.5362 | 0 | 0% | 30.1024 | 0 | 0% | 41.6687 | 0 | 0% | 53.235 | 0 | 0% | 64.8012 | 0 | 0% | 76.3675 | 0 | 0% | 64.8012 | 0 | 0% | 73.4759 | 0 | 0% | 82.1506 | 0 | 0% | 90.8253 | 0 | 0% | 99.5 | 0 | 0% | 87.9337 | 0 | 0% | 99.5 | 0 | 0%

## PLANNED (hidden)
DO NOT EDIT THE FIRST TABLE IN RED!! PLEASE ADD ONE TABLE IN DARK YELLOW FOR EACH PARTNER
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
ALL | 11.4444 | 15.6111 | 24.7798 | 24.7798 | 20.9953 | 28.6392 | 27.2392 | 23.4518 | 26.8464 | 22.7035 | 22.7035 | 23.9035 | 23.9035 | 23.9035 | 26.449 | 26.449 | 26.449 | 26.449 | 26.449 | 26.449 | 26.449 | 26.449 | 26.449 | 26.449 | 22.2747 | 22.2747 | 22.2747 | 18.4565 | 18.4565 | 18.4565 | 13.9977 | 13.9977 | 13.9977 | 9.8065 | 9.8065 | 9.8065 | 779
WP1 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 1.0694 | 38.5
WP2 | 8.25 | 12.4167 | 16.5595 | 16.5595 | 10.8095 | 10.8095 | 8.3095 | 4.1429 | 4.1429 | [27 empty] | 92
WP3 |  |  | 3.0909 | 3.0909 | 3.0909 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 7.14 | 4.0491 | 4.0491 | 4.0491 | 0.64 | 0.64 | 0.64 | [6 empty] | 159
WP4 | 0.58333 | 0.58333 | 1.0833 | 1.0833 | 1.0833 | 1.4924 | 1.4924 | 1.4924 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 2.447 | 1.3636 | 1.3636 | 1.3636 | 0.95455 | 0.95455 | 0.95455 | [6 empty] | 55
WP5 | [5 empty] | 3.1857 | 3.1857 | 3.1857 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 4.6257 | 2.2257 | 2.2257 | 2.2257 |  |  |  | 118
WP6 |  |  |  |  | 1.9655 | 1.9655 | 1.9655 | 1.9655 | 1.9655 | 1.9655 | 1.9655 | 3.1655 | 3.1655 | 3.1655 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 5.1201 | 3.1545 | 3.1545 | 3.1545 | 130
WP7 |  |  | 0.46429 | 0.46429 | 0.46429 | 0.46429 | 1.5643 | 1.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 2.5643 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 3.1552 | 2.6909 | 2.6909 | 2.6909 | 2.6909 | 2.6909 | 2.6909 | 87
WP8 | [36 empty] | 0
WP9 | [36 empty] | 0
WP10 | [36 empty] | 0
WP11 | 1.5417 | 1.5417 | 2.5123 | 2.5123 | 2.5123 | 2.5123 | 2.5123 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 2.8916 | 99.5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
ENG | 1.0278 | 1.3611 | 2.1447 | 2.1447 | 2.2051 | 3.1661 | 3.0661 | 2.7328 | 3.3599 | 2.7885 | 2.7885 | 2.9485 | 2.9485 | 2.9485 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.9939 | 2.1758 | 2.1758 | 2.1758 | 2.14 | 2.14 | 2.14 | 1.1668 | 1.1668 | 1.1668 | 91
WP1 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 0.55556 | 20
WP2 | 0.41667 | 0.75 | 1.3214 | 1.3214 | 1.0714 | 1.0714 | 0.90476 | 0.57143 | 0.57143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP3 | 0 | 0 | 0 | 0 | 0 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0.81818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.14286 | 0.14286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0.66286 | 0 | 0 | 0 | 17
WP6 | 0 | 0 | 0 | 0 | 0.31034 | 0.31034 | 0.31034 | 0.31034 | 0.31034 | 0.31034 | 0.31034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.47034 | 0.16 | 0.16 | 0.16 | 13
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.10238 | 0.10238 | 0.20952 | 0.20952 | 0.20952 | 0.20952 | 0.20952 | 0.20952 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.25498 | 0.21926 | 0.21926 | 0.21926 | 0.21926 | 0.21926 | 0.21926 | 7
WP8
WP9
WP10
WP11 | 0.055556 | 0.055556 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 0.23203 | 8
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
CERTH | 0.69444 | 0.86111 | 1.1537 | 1.1537 | 0.75715 | 1.2449 | 1.2449 | 1.1128 | 1.4709 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.3281 | 1.1538 | 1.1538 | 1.1538 | 1.0175 | 1.0175 | 1.0175 | 0.41929 | 0.41929 | 0.41929 | 0.20442 | 0.20442 | 0.20442 | 38
WP1 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
WP2 | 0.5 | 0.66667 | 0.80952 | 0.80952 | 0.30952 | 0.30952 | 0.30952 | 0.14286 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP3 | 0 | 0 | 0 | 0 | 0 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.32545 | 0.28 | 0.28 | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP4 | 0.083333 | 0.083333 | 0.17424 | 0.17424 | 0.17424 | 0.26515 | 0.26515 | 0.26515 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.58333 | 0.40909 | 0.40909 | 0.40909 | 0.31818 | 0.31818 | 0.31818 | 0 | 0 | 0 | 0 | 0 | 0 | 13
WP5 | 0 | 0 | 0 | 0 | 0 | 0.071429 | 0.071429 | 0.071429 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0.11143 | 0 | 0 | 0 | 3
WP6 | 0 | 0 | 0 | 0 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0 | 0 | 0 | 3
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8
WP9
WP10
WP11 | 0.055556 | 0.055556 | 0.11438 | 0.11438 | 0.11438 | 0.11438 | 0.11438 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 0.14886 | 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
RiSSC | 0.44444 | 0.44444 | 0.61671 | 0.61671 | 0.50464 | 0.50464 | 0.33798 | 0.40694 | 0.4524 | 0.30954 | 0.30954 | 0.62954 | 0.62954 | 0.62954 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.81136 | 0.7659 | 0.7659 | 0.7659 | 0.62797 | 0.62797 | 0.62797 | 24
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0.41667 | 0.41667 | 0.55952 | 0.55952 | 0.30952 | 0.30952 | 0.14286 | 0.14286 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 1
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0.13793 | 0.13793 | 0.13793 | 0.13793 | 0.13793 | 0.13793 | 0.13793 | 0.45793 | 0.45793 | 0.45793 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.63975 | 0.50182 | 0.50182 | 0.50182 | 16
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8
WP9
WP10
WP11 | 0.027778 | 0.027778 | 0.05719 | 0.05719 | 0.05719 | 0.05719 | 0.05719 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 0.12616 | 4
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
EXPSYS | 0.48611 | 0.48611 | 0.65838 | 0.65838 | 0.64976 | 0.64976 | 0.48309 | 0.51758 | 0.65394 | 0.51108 | 0.51108 | 0.91108 | 0.91108 | 0.91108 | 1.0929 | 1.0929 | 1.0929 | 1.0929 | 1.0929 | 1.0929 | 1.0929 | 1.0929 | 1.0929 | 1.0929 | 1.0512 | 1.0512 | 1.0512 | 1.0512 | 1.0512 | 1.0512 | 0.91487 | 0.91487 | 0.91487 | 0.67349 | 0.67349 | 0.67349 | 31
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0.41667 | 0.41667 | 0.55952 | 0.55952 | 0.30952 | 0.30952 | 0.14286 | 0.14286 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0.041667 | 0.041667 | 0.041667 | 0.041667 | 0.041667 | 0.041667 | 0.041667 | 0.041667 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.17803 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0.24138 | 0.24138 | 0.24138 | 0.24138 | 0.24138 | 0.24138 | 0.24138 | 0.64138 | 0.64138 | 0.64138 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.8232 | 0.58182 | 0.58182 | 0.58182 | 21
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8
WP9
WP10
WP11 | 0.027778 | 0.027778 | 0.05719 | 0.05719 | 0.05719 | 0.05719 | 0.05719 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 0.091672 | 3
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
AIT | 0.45833 | 1.125 | 1.2132 | 1.2132 | 1.0667 | 1.8394 | 1.8394 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 1.1727 | 0.40002 | 0.40002 | 0.40002 | 0.40002 | 0.40002 | 0.40002 | 0.29657 | 0.29657 | 0.29657 | 35.5
WP1 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 0.027778 | 1
WP2 | 0.25 | 0.91667 | 0.91667 | 0.91667 | 0.66667 | 0.66667 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
WP3 | 0 | 0 | 0 | 0 | 0 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0.77273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0 | 0 | 0 | 3
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8
WP9
WP10
WP11 | 0.18056 | 0.18056 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 0.26879 | 9.5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
IBEC | 0.54167 | 0.70833 | 0.97514 | 0.97514 | 0.97514 | 1.1351 | 1.0351 | 1.0409 | 1.1675 | 1.0247 | 1.0247 | 1.1847 | 1.1847 | 1.1847 | 1.4119 | 1.4119 | 1.4119 | 1.4119 | 1.4119 | 1.4119 | 1.4119 | 1.4119 | 1.4119 | 1.4119 | 1.3286 | 1.3286 | 1.3286 | 1.3286 | 1.3286 | 1.3286 | 1.042 | 1.042 | 1.042 | 1.042 | 1.042 | 1.042 | 42.5
WP1 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 0.097222 | 3.5
WP2 | 0.16667 | 0.33333 | 0.47619 | 0.47619 | 0.47619 | 0.47619 | 0.30952 | 0.14286 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WP3 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP4 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.17424 | 0.090909 | 0.090909 | 0.090909 | 0.090909 | 0.090909 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0.16 | 0.16 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 0.25091 | 6
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.10238 | 0.10238 | 0.1381 | 0.1381 | 0.1381 | 0.1381 | 0.1381 | 0.1381 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.27446 | 0.23874 | 0.23874 | 0.23874 | 0.23874 | 0.23874 | 0.23874 | 7
WP8
WP9
WP10
WP11 | 0.19444 | 0.19444 | 0.28268 | 0.28268 | 0.28268 | 0.28268 | 0.28268 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 0.45509 | 15
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
IIP | 0.70833 | 0.875 | 1.2841 | 1.2841 | 1.31 | 1.6281 | 1.4615 | 1.2948 | 1.6584 | 1.6584 | 1.6584 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.8184 | 1.201 | 1.201 | 1.201 | 0.88283 | 0.88283 | 0.88283 | 0.5192 | 0.5192 | 0.5192 | 0.24333 | 0.24333 | 0.24333 | 47
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0.41667 | 0.58333 | 0.58333 | 0.58333 | 0.33333 | 0.33333 | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WP3 | 0 | 0 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP4 | 0.20833 | 0.20833 | 0.43561 | 0.43561 | 0.43561 | 0.75379 | 0.75379 | 0.75379 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 1.1174 | 0.68182 | 0.68182 | 0.68182 | 0.36364 | 0.36364 | 0.36364 | 0 | 0 | 0 | 0 | 0 | 0 | 25
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0.27586 | 0.27586 | 0.27586 | 0.27586 | 0.27586 | 0.27586 | 0.27586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.43586 | 0.16 | 0.16 | 0.16 | 12
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8
WP9
WP10
WP11 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 0.083333 | 3
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
SYSTRAN | 0.22222 | 0.38889 | 0.76551 | 0.76551 | 0.86896 | 1.3495 | 1.3161 | 1.1495 | 1.3495 | 1.2066 | 1.2066 | 1.2066 | 1.2066 | 1.2066 | 1.2521 | 1.2521 | 1.2521 | 1.2521 | 1.2521 | 1.2521 | 1.2521 | 1.2521 | 1.2521 | 1.2521 | 1.1612 | 1.1612 | 1.1612 | 0.75208 | 0.75208 | 0.75208 | 0.60922 | 0.60922 | 0.60922 | 0.23434 | 0.23434 | 0.23434 | 35
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0.16667 | 0.33333 | 0.47619 | 0.47619 | 0.47619 | 0.47619 | 0.30952 | 0.14286 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
WP3 | 0 | 0 | 0.090909 | 0.090909 | 0.090909 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.40909 | 0.40909 | 0.40909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.071429 | 0.071429 | 0.071429 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0 | 0 | 0 | 7
WP6 | 0 | 0 | 0 | 0 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0 | 0 | 0 | 3
WP7 | 0 | 0 | 0.14286 | 0.14286 | 0.14286 | 0.14286 | 0.27619 | 0.27619 | 0.27619 | 0.27619 | 0.27619 | 0.27619 | 0.27619 | 0.27619 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.32165 | 0.17879 | 0.17879 | 0.17879 | 0.17879 | 0.17879 | 0.17879 | 9
WP8
WP9
WP10
WP11 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
TIU-JADS | 0.63889 | 0.80556 | 1.4003 | 1.4003 | 1.2537 | 1.5252 | 1.4918 | 1.3596 | 1.5596 | 1.4168 | 1.4168 | 1.4168 | 1.4168 | 1.4168 | 1.5986 | 1.5986 | 1.5986 | 1.5986 | 1.5986 | 1.5986 | 1.5986 | 1.5986 | 1.5986 | 1.5986 | 1.0683 | 1.0683 | 1.0683 | 1.0683 | 1.0683 | 1.0683 | 0.8683 | 0.8683 | 0.8683 | 0.49343 | 0.49343 | 0.49343 | 45
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0.41667 | 0.58333 | 0.72619 | 0.72619 | 0.47619 | 0.47619 | 0.30952 | 0.14286 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP3 | 0 | 0 | 0.36364 | 0.36364 | 0.36364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.56364 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 13
WP4 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP5 | 0 | 0 | 0 | 0 | 0 | 0.071429 | 0.071429 | 0.071429 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0.27143 | 0 | 0 | 0 | 7
WP6 | 0 | 0 | 0 | 0 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.10345 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.28527 | 0.18182 | 0.18182 | 0.18182 | 7
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 0.13333 | 4
WP8
WP9
WP10
WP11 | 0.055556 | 0.055556 | 0.14379 | 0.14379 | 0.14379 | 0.14379 | 0.14379 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 0.17827 | 6
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
DITSS | 0.83333 | 1.1667 | 1.7624 | 1.7624 | 1.0124 | 1.0124 | 1.1124 | 0.77902 | 1.2076 | 1.0647 | 1.0647 | 1.0647 | 1.0647 | 1.0647 | 1.1556 | 1.1556 | 1.1556 | 1.1556 | 1.1556 | 1.1556 | 1.1556 | 1.1556 | 1.1556 | 1.1556 | 0.97382 | 0.97382 | 0.97382 | 0.97382 | 0.97382 | 0.97382 | 0.93811 | 0.93811 | 0.93811 | 0.93811 | 0.93811 | 0.93811 | 39
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0.75 | 1.0833 | 1.2262 | 1.2262 | 0.47619 | 0.47619 | 0.47619 | 0.14286 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.13571 | 0.13571 | 0.56429 | 0.56429 | 0.56429 | 0.56429 | 0.56429 | 0.56429 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.65519 | 0.61948 | 0.61948 | 0.61948 | 0.61948 | 0.61948 | 0.61948 | 18
WP8
WP9
WP10
WP11 | 0.083333 | 0.083333 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 0.31863 | 11
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
VIAS | 0.38889 | 0.38889 | 0.38889 | 0.38889 | 0.9751 | 0.9751 | 0.64176 | 0.67625 | 0.67625 | 0.67625 | 0.67625 | 0.67625 | 0.67625 | 0.67625 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 1.1762 | 0.59004 | 0.59004 | 0.59004 | 33
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | 0 | 0 | 0 | 0 | 0.58621 | 0.58621 | 0.58621 | 0.58621 | 0.58621 | 0.58621 | 0.58621 | 0.58621 | 0.58621 | 0.58621 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 1.0862 | 0.5 | 0.5 | 0.5 | 28
WP7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8
WP9
WP10
WP11 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 0.090038 | 3
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
KWPG | 0.83333 | 1.1667 | 2.0695 | 2.0695 | 1.5695 | 2.2682 | 2.2015 | 1.8682 | 2.0196 | 1.591 | 1.591 | 1.591 | 1.591 | 1.591 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.3637 | 1.3637 | 1.3637 | 1.1365 | 1.1365 | 1.1365 | 0.70075 | 0.70075 | 0.70075 | 0.54933 | 0.54933 | 0.54933 | 53
WP1 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
WP2 | 0.66667 | 1 | 1.4286 | 1.4286 | 0.92857 | 0.92857 | 0.7619 | 0.42857 | 0.42857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP3 | 0 | 0 | 0.40909 | 0.40909 | 0.40909 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.22727 | 0.22727 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.47143 | 0.47143 | 0.47143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.15143 | 0.15143 | 0.15143 | 0 | 0 | 0 | 14
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 3
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.13571 | 0.13571 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 7
WP8
WP9
WP10
WP11 | 0.11111 | 0.11111 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
AoC | 0.83333 | 1.1667 | 2.0695 | 2.0695 | 1.5695 | 2.2682 | 2.2015 | 1.8682 | 2.0196 | 1.591 | 1.591 | 1.591 | 1.591 | 1.591 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.3637 | 1.3637 | 1.3637 | 1.1365 | 1.1365 | 1.1365 | 0.70075 | 0.70075 | 0.70075 | 0.54933 | 0.54933 | 0.54933 | 53
WP1 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
WP2 | 0.66667 | 1 | 1.4286 | 1.4286 | 0.92857 | 0.92857 | 0.7619 | 0.42857 | 0.42857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP3 | 0 | 0 | 0.40909 | 0.40909 | 0.40909 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.22727 | 0.22727 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.47143 | 0.47143 | 0.47143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.15143 | 0.15143 | 0.15143 | 0 | 0 | 0 | 14
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 3
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.13571 | 0.13571 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 7
WP8
WP9
WP10
WP11 | 0.11111 | 0.11111 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
CAST | 0.83333 | 1.1667 | 2.0695 | 2.0695 | 1.5695 | 2.2682 | 2.2015 | 1.8682 | 2.0196 | 1.591 | 1.591 | 1.591 | 1.591 | 1.591 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.3637 | 1.3637 | 1.3637 | 1.1365 | 1.1365 | 1.1365 | 0.70075 | 0.70075 | 0.70075 | 0.54933 | 0.54933 | 0.54933 | 53
WP1 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
WP2 | 0.66667 | 1 | 1.4286 | 1.4286 | 0.92857 | 0.92857 | 0.7619 | 0.42857 | 0.42857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP3 | 0 | 0 | 0.40909 | 0.40909 | 0.40909 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.22727 | 0.22727 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.47143 | 0.47143 | 0.47143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.15143 | 0.15143 | 0.15143 | 0 | 0 | 0 | 14
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 3
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.13571 | 0.13571 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 7
WP8
WP9
WP10
WP11 | 0.11111 | 0.11111 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
NPN | 0.83333 | 1.1667 | 2.0695 | 2.0695 | 1.5695 | 2.2682 | 2.2015 | 1.8682 | 2.0196 | 1.591 | 1.591 | 1.591 | 1.591 | 1.591 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.3637 | 1.3637 | 1.3637 | 1.1365 | 1.1365 | 1.1365 | 0.70075 | 0.70075 | 0.70075 | 0.54933 | 0.54933 | 0.54933 | 53
WP1 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
WP2 | 0.66667 | 1 | 1.4286 | 1.4286 | 0.92857 | 0.92857 | 0.7619 | 0.42857 | 0.42857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP3 | 0 | 0 | 0.40909 | 0.40909 | 0.40909 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.22727 | 0.22727 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.47143 | 0.47143 | 0.47143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.15143 | 0.15143 | 0.15143 | 0 | 0 | 0 | 14
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 3
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.13571 | 0.13571 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 7
WP8
WP9
WP10
WP11 | 0.11111 | 0.11111 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
GDCOC | 0.83333 | 1.1667 | 2.0695 | 2.0695 | 1.5695 | 2.2682 | 2.2015 | 1.8682 | 2.0196 | 1.591 | 1.591 | 1.591 | 1.591 | 1.591 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.3637 | 1.3637 | 1.3637 | 1.1365 | 1.1365 | 1.1365 | 0.70075 | 0.70075 | 0.70075 | 0.54933 | 0.54933 | 0.54933 | 53
WP1 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
WP2 | 0.66667 | 1 | 1.4286 | 1.4286 | 0.92857 | 0.92857 | 0.7619 | 0.42857 | 0.42857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP3 | 0 | 0 | 0.40909 | 0.40909 | 0.40909 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.22727 | 0.22727 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.47143 | 0.47143 | 0.47143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.15143 | 0.15143 | 0.15143 | 0 | 0 | 0 | 14
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 3
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.13571 | 0.13571 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 7
WP8
WP9
WP10
WP11 | 0.11111 | 0.11111 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 5
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
LPV | 0.83333 | 1.1667 | 2.0695 | 2.0695 | 1.5695 | 2.2682 | 2.2015 | 1.8682 | 2.0196 | 1.591 | 1.591 | 1.591 | 1.591 | 1.591 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.7728 | 1.3637 | 1.3637 | 1.3637 | 1.1365 | 1.1365 | 1.1365 | 0.70075 | 0.70075 | 0.70075 | 0.54933 | 0.54933 | 0.54933 | 53
WP1 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 0.055556 | 2
WP2 | 0.66667 | 1 | 1.4286 | 1.4286 | 0.92857 | 0.92857 | 0.7619 | 0.42857 | 0.42857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
WP3 | 0 | 0 | 0.40909 | 0.40909 | 0.40909 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.63636 | 0.22727 | 0.22727 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0.47143 | 0.47143 | 0.47143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.55143 | 0.15143 | 0.15143 | 0.15143 | 0 | 0 | 0 | 14
WP6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 0.13636 | 3
WP7 | 0 | 0 | 0.035714 | 0.035714 | 0.035714 | 0.035714 | 0.13571 | 0.13571 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.20714 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.2526 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 0.21688 | 7
WP8
WP9
WP10
WP11 | 0.11111 | 0.11111 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 0.14052 | 5

## GANTT
[24 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[24 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | ENG | CERTH | RiSSC | EXPSYS | AIT | IBEC | IIP | SYSTRAN | TIU-JADS | DITSS | VIAS | KWPG | AoC | CAST | NPN | GDCOC | LPV | TOTAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG |  | Project Management | 23 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 4 | 1 | 1 | 1 | 47 | 1 | 36
WP1 | ENG | 1.1 | Project organisation & management | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 24 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 7 | 1 | 36
WP2 | RiSSC |  | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 2 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 53 | 1 | 36
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 17 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 17 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 19 | 13 | 30
WP3 | IIP |  | Social, Ethical, Legal and Privacy issues of online sources analysis | 3 | 3 |  |  |  |  | 22 | [10 empty] | 28 | 1 | 36
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | [5 empty] | 3 | [10 empty] | 3 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 1 | [5 empty] | 5 | [10 empty] | 6 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 2 |  |  |  |  | 6 | [10 empty] | 8 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 2 | 1 |  |  |  |  | 8 | [10 empty] | 11 | 1 | 36
WP4 | CERTH |  | Use cases, Requirements and System Architecture | 6 | 8 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 36 | 1 | 21
WP4 | CAST | 4.1 | User requirements, use cases and scenarios |  | 3 | 1 | [6 empty] | 2 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 15 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 2 | 4 |  | 1 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 12 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 4 | 1 |  | 1 | 1 | 1 |  | 1 | [9 empty] | 9 | 4 | 21
WP5 | AIT |  | Data sources and analysis stream | 8 |  | 2 | 9 | 20 |  |  |  | 8 | [8 empty] | 47 | 1 | 27
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 2 |  | 2 |  | 2 |  |  |  | 8 | [8 empty] | 14 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 2 |  |  |  | 6 | [12 empty] | 8 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 2 |  |  | 8 | [13 empty] | 10 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 |  |  |  | 6 | [12 empty] | 6 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 2 |  |  | 1 | 6 | [12 empty] | 9 | 4 | 27
WP6 | CERTH |  | Big Data analysis and analytics | 6 | 19 |  | 18 |  |  |  | 17 | 8 | [8 empty] | 68 | 4 | 30
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 6 |  |  | 18 | [13 empty] | 24 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 8 | [15 empty] | 8 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | [6 empty] | 8 | [9 empty] | 8 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | [6 empty] | 9 | [9 empty] | 9 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 2 | [6 empty] | 8 | [8 empty] | 10 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 9 | [15 empty] | 9 | 4 | 30
WP7 | EXPSYS |  | Knowledge management and reasoning | 24 | 12 |  | 24 | 5 | [12 empty] | 65 | 7 | 30
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 2 |  |  | 8 | [13 empty] | 10 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 4 |  |  | 10 | 3 | [12 empty] | 17 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 10 |  |  | 6 | 2 | [12 empty] | 18 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 8 | [16 empty] | 8 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation |  | 12 | [15 empty] | 12 | 7 | 30
WP8 | IBEC |  | Integration of human factor in the analysis loop | 0 | 18 |  | 1 |  | 32 |  | 1 | [9 empty] | 52 | 4 | 30
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 2 |  |  |  | 10 | [11 empty] | 12 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 |  |  |  |  | 10 | [11 empty] | 10 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 14 |  | 1 |  | 4 |  | 1 | [9 empty] | 20 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 2 |  |  |  | 8 | [11 empty] | 10 | 16 | 30
WP9 | ENG |  | Novel applications for LEAs and System Integration | 40 | 2 |  | 4 | 3 | 5 |  | 2 | 2 | [8 empty] | 58 | 7 | 33
WP9 | ENG | 9.1 | Big Data Infrastructure | 6 |  |  |  | 1 | [12 empty] | 7 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 9 | [16 empty] | 9 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 8 |  |  |  |  | 3 | [11 empty] | 11 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 6 | [16 empty] | 6 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 10 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | [8 empty] | 16 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 1 | 1 |  | 3 | 1 | 1 |  | 1 | 1 | [8 empty] | 9 | 16 | 33
WP10 | DITSS |  | Demonstration in relevant environment | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 11 | 7 | 8 | 10 | 6 | 5 | 6 | 4 | 87 | 10 | 36
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 21 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 21 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 4 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 24 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 1 | 2 | 4 | 1 | 1 | 2 | 1 | 21 | 22 | 36
WP11 | AoC |  | Dissemination, Training and Exploitation | 7 | 4 | 8 | 6 | 3 | 4 | 1 | 3 | 3 | 6 | 3 | 5 | 11 | 5 | 3 | 4 | 3 | 79 | 1 | 36
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 19 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 1 |  | 2 | [5 empty] | 1 | 3 | 1 |  |  | 1 |  |  |  | 9 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 |  | 3 |  |  | 1 |  |  | 1 |  |  | 2 | 4 | 2 | 1 | 1 | 1 | 16 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 |  | 2 | 3 | 1 | 1 | 2 | 1 | 17 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 1 | 1 | 1 | 1 | [5 empty] | 1 | 1 |  | 3 |  |  |  |  | 9 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 3 | 1 | 1 | 1 | 1 | 1 |  | 1 | [9 empty] | 9 | 13 | 36

## ENG
ENG | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 23 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 10 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 8 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 2 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 3 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 2 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 2 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 1 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 2 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 6 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 0 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 2 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 4 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream | 8 | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 2 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 2 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 2 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 2 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics | 6 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 6 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning | 24 | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 2 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 4 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 10 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 8 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop | 0 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration | 40 | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 6 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 9 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 8 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 6 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 10 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 1 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 4 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 7 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 1 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 1 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 3 | 0 | 13 | 36
| DATE |  | NOTES

## CERTH
CERTH | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 5 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 4 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 2 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 1 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 8 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 3 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 4 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 1 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics | 19 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 8 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 2 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 9 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning | 12 | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 12 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop | 18 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 2 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 14 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 2 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration | 2 | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 1 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 1 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 4 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 4 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 1 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 1 | 0 | 13 | 36
| DATE |  | NOTES

## RiSSC
RiSSC | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 30 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 10 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 10 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 10 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 1 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream | 2 | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 2 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 4 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 8 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 2 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 3 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 0 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 1 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 1 | 0 | 13 | 36
| DATE |  | NOTES

## EXPSYS
EXPSYS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 2 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 0 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 1 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 1 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream | 9 | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 8 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 1 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics | 18 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 18 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning | 24 | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 8 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 10 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 6 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop | 1 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 1 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration | 4 | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 1 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 3 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 4 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 6 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 3 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 1 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 1 | 0 | 13 | 36
| DATE |  | NOTES

## AIT
AIT | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 2 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 0 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 1 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 1 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream | 20 | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 2 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 6 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 6 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 6 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning | 5 | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 3 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 2 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration | 3 | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 1 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 1 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 1 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 4 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 1 | 0 | 13 | 36
| DATE |  | NOTES

## IBEC
IBEC | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 2 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 0 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 1 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 1 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop | 32 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 10 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 10 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 4 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 8 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration | 5 | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 3 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 1 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 1 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 4 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 4 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 1 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 1 | 0 | 13 | 36
| DATE |  | NOTES

## IIP
IIP | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis | 22 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 3 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 5 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 6 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 8 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 0 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 1 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 2 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 0 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 0 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 0 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## SYSTRAN
SYSTRAN | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 2 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 0 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 1 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 1 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics | 17 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 8 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 9 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop | 1 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 1 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration | 2 | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 1 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 1 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 2 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 0 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 0 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 1 | 0 | 13 | 36
| DATE |  | NOTES

## TIU-JADS
TIU-JADS | [7 empty] | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 0 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 1 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream | 8 | 2 | 1 | 27 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 8 | 2 | 1 | 18 | 2018 May: 0.4; 2018 Jun: 0.4; 2018 Jul: 0.4; 2018 Aug: 0.4; 2018 Sep: 0.4
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics | 8 | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 8 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration | 2 | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 1 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 1 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 2 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 0 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 0 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 1 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 1 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 0 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## DITSS
DITSS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 1 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 1 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 1 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 2 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 2 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 11 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 2 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 3 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 4 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 2 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 6 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 3 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 1 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## VIAS
VIAS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 2 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 1 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 0 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 0 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 0 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 0 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 1 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 7 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 2 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 2 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 2 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 1 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 0 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 0 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 1 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## KWPG
KWPG | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 1 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 1 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 1 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 1 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 8 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 2 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 2 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 2 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 2 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 5 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 2 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 2 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## AoC
AoC | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 1 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 1 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 1 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 1 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 10 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 2 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 2 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 2 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 4 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 11 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 4 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 3 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 3 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## CAST
CAST | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 4 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 3 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 1 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 1 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 1 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 3 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 3 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 6 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 3 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 5 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 1 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 2 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## NPN
NPN | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 1 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 1 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 1 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 1 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 5 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 2 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 1 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## GDCOC
GDCOC | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 1 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 1 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 1 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 1 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 6 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 2 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 2 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 4 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 1 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 2 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## LPV
LPV | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
[8 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
WP | WP Leader | T | Name of the WP/Task | GRANTED | ACTUAL | FROM | TO | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | ENG | 0 | Project Management | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | ENG | 1.1 | Project organisation & management | 0 | 0 | 1 | 36
WP1 | ENG | 1.2 | Project progress and cost reporting | 1 | 0 | 1 | 36
WP1 | CERTH | 1.3 | Quality management | 0 | 0 | 1 | 36
WP1 | ENG | 1.4 | Security aspects management | 0 | 0 | 1 | 36
WP2 | RiSSC | 0 | Interdisciplinary analysis of online illegal trafficking and study of strategies and countermeasures | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | RiSSC | 2.1 | Criminological analysis and knowledge generation on online illegal trafficking | 1 | 0 | 1 | 36
WP2 | RiSSC | 2.2 | Criminal human factor involved in the online illegal trafficking | 1 | 0 | 4 | 18
WP2 | RiSSC | 2.3 | Criminal scenarios and profiling | 1 | 0 | 13 | 30
WP3 | IIP | 0 | Social, Ethical, Legal and Privacy issues of online sources analysis |  | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | IIP | 3.1 | European data protection framework analysis | 0 | 0 | 1 | 10
WP3 | IIP | 3.2 | Online sources analysis and cooperation with LEAs | 0 | 0 | 7 | 24
WP3 | IIP | 3.3 | Data Control | 0 | 0 | 1 | 36
WP3 | IIP | 3.4 | Ethics and privacy impact assessment and mitigation measures | 0 | 0 | 1 | 36
WP4 | CERTH | 0 | Use cases, Requirements and System Architecture | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | CAST | 4.1 | User requirements, use cases and scenarios | 1 | 0 | 1 | 6
WP4 | CERTH | 4.2 | System specification | 0 | 0 | 1 | 9
WP4 | ENG | 4.3 | System architecture | 0 | 0 | 4 | 21
WP5 | AIT | 0 | Data sources and analysis stream |  | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | TIU-JADS | 5.1 | Data source risk assessment in the Surface Web, Deep Web and Dark Nets | 0 | 0 | 1 | 18
WP5 | AIT | 5.2 | Black markets discovery and monitoring | 0 | 0 | 4 | 27
WP5 | EXPSYS | 5.3 | Content acquisition from Surface Web and pre-processing | 0 | 0 | 4 | 27
WP5 | AIT | 5.4 | Blockchain analysis for illicit activity discovering | 0 | 0 | 4 | 27
WP5 | AIT | 5.5 | Construction of source network and filtering | 0 | 0 | 4 | 27
WP6 | CERTH | 0 | Big Data analysis and analytics |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP6 | EXPSYS | 6.1 | Multilingual Text analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.2 | Image and Video analysis | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.3 | Multilingual automated translation | 0 | 0 | 4 | 30
WP6 | SYSTRAN | 6.4 | Multilingual speech to text | 0 | 0 | 4 | 30
WP6 | TIU-JADS | 6.5 | Illegal trafficking trend analysis | 0 | 0 | 4 | 30
WP6 | CERTH | 6.6 | Visual Indexing | 0 | 0 | 4 | 30
WP7 | EXPSYS | 0 | Knowledge management and reasoning |  | 0 | 7 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP7 | EXPSYS | 7.1 | Knowledge modelling for illegal trafficking | 0 | 0 | 7 | 15
WP7 | EXPSYS | 7.2 | Black markets and illegal shops and products tracking | 0 | 0 | 7 | 30
WP7 | ENG | 7.3 | Reasoning mechanisms for Criminal network reconstruction | 0 | 0 | 7 | 30
WP7 | ENG | 7.4 | Knowledge based browsing, search and retrieval | 0 | 0 | 7 | 30
WP7 | CERTH | 7.5 | Extraction of evolving knowledge from deep neural network representation | 0 | 0 | 7 | 30
WP8 | IBEC | 0 | Integration of human factor in the analysis loop |  | 0 | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP8 | IBEC | 8.1 | Implicit and explicit user feedback capturing | 0 | 0 | 4 | 20
WP8 | IBEC | 8.2 | Adaptive user modelling for cognitive states estimation | 0 | 0 | 4 | 30
WP8 | CERTH | 8.3 | Incorporation of conscious and subconscious user feedback in deep learning representations | 0 | 0 | 4 | 30
WP8 | IBEC | 8.4 | Knowledge transfer to new officers | 0 | 0 | 16 | 30
WP9 | ENG | 0 | Novel applications for LEAs and System Integration |  | 0 | 7 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP9 | ENG | 9.1 | Big Data Infrastructure | 0 | 0 | 7 | 15
WP9 | ENG | 9.2 | Novel applications for illegal trafficking | 0 | 0 | 7 | 33
WP9 | ENG | 9.3 | Advanced Big Data Visual Analytics | 0 | 0 | 13 | 33
WP9 | ENG | 9.4 | Chain of custody and evidence export | 0 | 0 | 13 | 33
WP9 | ENG | 9.5 | Continuous System Integration | 0 | 0 | 7 | 33
WP9 | EXPSYS | 9.6 | System validation | 0 | 0 | 16 | 33
WP10 | DITSS | 0 | Demonstration in relevant environment | 4 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP10 | CAST | 10.1 | Pilot scenario definition | 1 | 0 | 10 | 15
WP10 | DITSS | 10.2 | Pilot preparation and planning | 1 | 0 | 13 | 21
WP10 | DITSS | 10.3 | Pilot execution | 1 | 0 | 22 | 36
WP10 | AoC | 10.4 | Evaluation and assessment | 1 | 0 | 22 | 36
WP11 | AoC | 0 | Dissemination, Training and Exploitation | 3 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP11 | EXPSYS | 11.1 | Dissemination and communication | 1 | 0 | 1 | 36
WP11 | DITSS | 11.2 | LEAs and stakeholders community engagement and management | 0 | 0 | 1 | 36
WP11 | CAST | 11.3 | Best Practice and guidelines for curricula | 1 | 0 | 18 | 36
WP11 | AoC | 11.4 | Training activities | 1 | 0 | 22 | 36
WP11 | AoC | 11.5 | Organisation of Workshops | 0 | 0 | 23 | 36
WP11 | ENG | 11.6 | Exploitation | 0 | 0 | 13 | 36
| DATE |  | NOTES

## Foglio4 (hidden)
| 2016-10-01 |  | 2016-11-01 |  | 2016-12-01 |  | 2017-01-01 |  | 2017-02-01 |  | 2017-03-01
Dipendenti | Ore | Costo pers + Ovhd | Ore | Costo pers + Ovhd | Ore | Costo pers + Ovhd | Ore | Costo pers + Ovhd | Ore | Costo pers + Ovhd | Ore | Costo pers + Ovhd
Alberti | [6 empty] | 102 | 3768.9 | 128 | 4729.6 | 124 | 4581.8
Canducci | 32 | 2824 | 24 | 2118 | 16 | 1412 | 40 | 3530 | 40 | 3530 | 40 | 3530
Cantore | [8 empty] | 32 | 499.6
Marguglio | 40 | 1423 | 24 | 853.8 | 16 | 569.2 | 24 | 853.8 | 48 | 1707.6 | 28 | 996.1